## Φύλλο1
2nd REPETITIVE - TECHNICAL SPECIFICATIONS & TERMS
REPAIR OF ONE (1) TRAVELLING BOOGIE WITH TWO WHEELS OF THE 30 TONS CRANE OF F/D PIRAEUS III
α.α. | Περιγραφή (Description) | μονάδα (unit) | ποσότητα (quantity) | τιμή μονάδας (Estimated unit value) | προϋπολογισμός (Estimated total value)
1 | Description of requested works: Dismantling of the boogie and of the intermediate gear. Transportation of the parts to the contractor's workshop. Full dismantling of the parts, cleaning, optical inspection and conduction of measurements. Replacement of all necessary parts. Assembly of boogie and transportation of the parts back to the F/D III. Assembly of boogie, intermediate gear, gear box, brake and electric motor on their position on the crane. Reassembly of the rest crane's parts. Test of the machinery's good operation. | work | 1
Total ( Σύνολο ) : €
V.A.T. ( 24% ) : €
GRAND TOTAL : €
REMARKS:
1 | All the necessary meterials / spare parts will be provided by PPA S.A. or by the Contractor, following the disassembly by the Contractor & the inspection of the parts by PPA S.A., the submission of an extra relevant offer by the Contractor and the offer's acceptance by PPA S.A. The extra cost of the materials/parts to be used/replaced is not included in the cost of the above-mentioned described works as it is not known prior to the disassembly.
2 | All aforementioned repair work must be completed within five (5) calendar days.
3 | Prior to the commencement of the repair works, a PPA committee (established by Engineering department's DCEO) will perform an onsite inspection at the contractor's workshop in order to inspect the internal damage of the parts and identify & finally decide which parts need to be replaced. The outcome of the inspection (report) will be attached to the respective Payment Approval and will constitute a necessary provision for the Contractor's invoice payment.
4 | Αward criteriοn: The lowest price for the total of works herein described.
4 | Candidates may visit PPA S.A. premises (F/D Piraeus III) in order to inspect the Crane and be further informed regarding the requested works. Contact persons for the visit: Georgoutsos Al. (210 4090583) and Georgiadis Chr. (210 4090589).
5 | Attached drawings (HW 3026-30_Crane General Arrangement and HW 3026-13_Assembly of travelling device)
6 | Terms of payment: within two (2) months upon invoicing and following acceptance of the works by competent PPA S.A. acceptance body.
7 | Offer validity: at least two (2) months
8 | Insurance policy: Each Candidate has to submit (within the offer's technical folder) relevant proof of the Contractors All Risk insurance policy, including copies of the insurance certificate and policy documents