## εξ.
中远海运比雷埃夫斯港口有限公司
PIRAEUS PORT AUTHORITY S.A.
ΟΡΓΑΝΙΣΜΟΣ ΛΙΜΕΝΟΣ ΠΕΙΡΑΙΩΣ Α.Ε.
ANNEX A
ENGINEERING DEPARTMENT
TECHNICAL DESCRIPTION – GENERAL TERMS & REMARKS
REMOVAL AND INSTALLATION OF X-RAY & MAGNETIC GATES FOR THE NEEDS OF PPA SA

## TECHNICAL DESCRIPTION
P.P.A. S.A - ENGINEERING DEPARTMENT REMOVAL AND INSTALLATION OF X-RAY & MAGNETIC GATES FOR THE NEEDS OF PPA SA |  |  |  |  | ANNEX A I TECHNICAL DESCRIPTION – GENERAL TERMS & REMARKS
LOT | A/A | Περιγραφή Description | Μονάδα Unit | Ποσότητες Quantity | Τιμή Μονάδας Unit Price | Ολική TOTAL COST
1 | 1 | Removal and Installation of X-Ray equipment HS-6040i, OEM Smiths Detection | pc | 3 |  | 0
| 2 | Removal and Installation of X-Ray equipment HS-7555i, OEM Smiths Detection | pc | 1 |  | 0
| 3 | Removal and Installation of Magnetic gates, OEM CEIA | pc | 7 |  | 0
2 | 4 | Removal and Installation of X-Ray equipment CX, OEM Nuctech | pc | 5 |  | 0
ΣΥΝΟΛΟ ΚΟΣΤΟΣ (ΧΩΡΙΣ Φ.Π.Α.) TOTAL COST (WITHOUT VAT) | [5 empty] | 0
Φ.Π.Α. 24% VAT 24% | [5 empty] | 0
ΓΕΝΙΚΟ ΣΥΝΟΛΟ (ΜΕ Φ.Π.Α.) GRAND TOTAL (WITH VAT) | [5 empty] | 0
GENERAL TERMS & REMARKS
1 | Scope of works
PPA will undertake the complete transportation of the X-ray and Magnetic gates equipment and prepare the new site, including creating the required apertures.
The awarded candidate will undertake the decommissioning, electrical isolation, mechanical reassembly, electrical integration, device parameterization, and subsequent adherence to the original equipment manufacturer's installation protocol, followed by final testing in the new location.
Installation the X-ray unit according to the manufacturer's instructions.
Securely mount the unit to the floor.
Ensure proper alignment and stability.
Integrate the X-ray unit with any necessary peripheral devices (e.g., computer, monitor, control panel).
2 | Quality Control Checks
Perform visual inspections of all connections and wiring.
Check for any signs of damage or malfunction.
Conduct performance tests to ensure the X-ray unit meets all manufacturer specifications and relevant safety standards.
This may include image quality tests, radiation safety checks, and functional tests.
3 | Award Criteria and LOT Structure
Award criterion shall be the lowest price per LOT (LOT 1: Items 1,2 & 3, LOT 2: Item 4), provided that all relevant requested terms and conditions are met. Selective Bidding within a LOT is not allowed, candidates are permitted to submit separate offers for LOT 1: items N°1 to N°3 and a separate offer for LOT 2 item N°4. Interested candidates may submit offer for one (1) or more lots.
4 | Financial Offer (Transportation and Installation Considerations)
Since the transportation and installation of the equipment can be carried out outside regular working hours (08:00 - 16:00), including weekends or public holidays, candidates must include these considerations in their offer. Submitting a separate offer for these activities is not permitted.
5 | Offer Validity
Offers shall be valid and binding the candidates for two (2) calendar months from the offer’s submission deadline.
6 | Certification Requirements from OEMs
Candidates must provide evidence from the OEMs of the X-ray and magnetic gates, demonstrating certifications for the installation and setup of such equipment.
7 | Decommissioning Schedule
The awarded candidate shall commence the decommissioning within two (2) working days from a formal notification by standard electronic means provided by Engineering Department or Cruise Department of PPA SA regarding the scheduled decommissioning date(s). Additionally, all services, including removal, installation, and quality control checks, must be fully completed within one (1) month from the start date specified in the signed contract.
8 | Payment Terms
The payment will be processed within two (2) calendar months following project finalization and from the issuance of the invoice, subject to the acceptance of the services by Engineering Department of PPA SA.
9 | Insurance Coverage
The awarded candidate is obligated to ensure full insurance coverage for their own civil liability and/or that of their appointees, as well as for the equipment used in the provision of their services. The insurance policy must include Third Party Liability coverage (vessels are considered third parties). Additionally, alongside PPA SA, the Hellenic Republic shall be named as an additional insured party in all the aforementioned coverages, in accordance with Article 17 of the Concession Agreement between the Hellenic Republic and PPA SA, as ratified by Law 4404/2016 (Government Gazette 126/8-7-2016). The contractor shall be insured by one or more insurance companies that are legally operating within the European Union. General Civil Liability a. Bodily injury / death per incident: 250,000.00 € b. Property damage per incident: 500,000.00 € c. Group Accident (Bodily injuries/death and Property damage per incident): 1,000,000.00 €, which represents the maximum limit of the policy during the execution of the works. Employer’s Liability a. Bodily injury / death per incident: 500,000.00 € b. Maximum liability limit: 500,000.00 € / Total Maximum Liability of the Company for compensation: 500,000.00 €
Supplier’s authorized stamp and signature over printed name
Signature:
Name:
Date: